## Replan Schedule & Staffing
Phase | [5 empty] | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Week Start Date (Monday) [Proposed] |  |  |  | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28
Plan,script and execute all SPRINTS 1-10 (End To End Testing of all integrated sprint functionality for Go-Live)
6/12 - Sprint 8 functionally stable (1 week after 6/2 "demo" target)
7/10 - Sprint 9 functionally stable (1 week after 6/30 "Demo" target)
8/7 - Sprint 10 functionally stable (1 week after 7/28 "Demo" target)
Environment Pre-Reqs Completed (See Below) | bar: 2017-06-19
Planning | bar: 2017-06-26 to 2017-07-10
Interview SME and collect requirements | bar: 2017-06-26 to 2017-07-10
Validate requirements | bar: 2017-06-26 to 2017-07-10
Develop Detailed Test Plan | bar: 2017-06-26 to 2017-07-10
Review and finalize Test Plan | bar: 2017-06-26 to 2017-07-10
Setup Load Test Tools | bar: 2017-06-26 to 2017-07-10
Engage Testers, get access / on board | bar: 2017-06-26 to 2017-07-10
Validate Environment and Access | bar: 2017-06-26 to 2017-07-10
Smoke Test App (Few basic flows and validate app data) | bar: 2017-06-26 to 2017-07-10
Prepare | bar: 2017-07-10 to 2017-07-31
Validate Functionality of Business Scenarios to script | bar: 2017-07-10 to 2017-07-31
Validate Test Data (transactional and user access data) | bar: 2017-07-10 to 2017-07-31
Setup/Validate Test Tool Infrastructure (test load drivers) | bar: 2017-07-10 to 2017-07-31
Test Script Creation (Web, iOS, UX) | bar: 2017-07-10 to 2017-07-31
Validate scripts | bar: 2017-07-10 to 2017-07-31
Conduct Test Readiness Review | bar: 2017-07-10 to 2017-07-31
Execute | bar: 2017-07-31 to 2017-08-21
Execute Baseline, 10% - 100% Peak Load Testing | bar: 2017-07-31 to 2017-08-21
Report - Prepare & Present Final Report | bar: 2017-08-21
Role | Resource Location |  | Rate |  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 |  | Total
Performance Lead | US |  | 140 |  |  | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 |  | 50400
Perf Tester #1 | IN |  | 24 |  |  | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 |  | 8640
Perf Tester #2 | IN |  | 22 |  |  | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 |  | 7920
Perf Tester #3 | IN |  | Existing Func Automation Resource |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  | Total Cost ==> |  |  | 7440 | 7440 | 7440 | 7440 | 7440 | 7440 | 7440 | 7440 | 7440 |  | 66960
|  |  | Start | End | Activity Description:
Environment Pre-Reqs |  |  | 2017-05-22 | 2017-06-23 | WFS System Admin Team & Development Team >> To Start and Complete the following: * Environment setup for Performance Testing * Sync Mobile App Build to Perf Environment * Setup/Loading of production like data volumes * Test Data for Performance Test Scripts must be established to facilitate Performance Test Scripting (and full set of Test Data to be ready by Test Execution start) * Configuration of any APP dependencies - like third party interfaces ,Stub etc. * Setup Env monitoring tools
Original Plan: Why the cost is so high now?
1. We were advised to start now (vs. later). Get a jump start on Perf testing up thru Build 7
2. The Test Schedule was derived based on current development schedules for Sprint 1-7 and Sprint 8-10. Test schedules were interlocked with Dev team (Mike McLeod). This plan was presented at 5/23 WFS workshop.
3. Build 8, 9, 10 arrive late in Testing schedule (weeks 7-9), and will trigger anticipated modifications to performance business scenarios/test scripts.
3. Combining the above points yields the original 13 week plan.
New Plan: | 1. Reduced timeline to 9 weeks (correlates to "generic" project plan shown in the April 7 meeting)
2. Dropping the "early" Sprint 1-7 Performance Test Phase/Focus
3. Alligning test schedules around Build 8, 9, 10 delivery schedules.
3. Risks:
| 1 | Issues identified during Performance Testing may prevent Dev Team from fixing prior to Go-Live
| 2 | Sprint 10 Code functions may introduce code & UI changes, resulting in breakage to existing Performance Test scripts. Could result in delays to execution schedule impacting go-live
| 3 | Not enough reaction time if perf test tool presents issues; The plan assumes perfect situation and in many cases it is not.

## Original Schedule & Staffing
Phase |  |  |  |  | Prep Week1 | Prep Week2 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13
Week Start Date (Monday) [Proposed] |  |  |  |  | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28
[7 empty] | Plan,script and execute : SPRINT 1-7 | [6 empty] | Plan,script and execute all SPRINTS 1-10 (End To End Testing of all integrated sprint functionality for Go-Live)
[11 empty] | Test execution of Sprints 1-7 |  |  |  | Test execution of Sprints 1-10
[13 empty] | * SPRINT 8&9, ** SPRINT 10 | * Sprint 8 & 9 "Functional QA" Validated
** Sprint 10 be ready for testing by July 31st
Environment Pre-Reqs (See Activity/Milestone summary below) | bar: 2017-05-22 to 2017-06-05; 2017-07-17
Planning | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Interview SME and collect requirements | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Validate requirements | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Develop Detailed Test Plan | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Review and finalize Test Plan | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Setup Load Test Tools | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Engage Testers, get access / on board | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Validate Environment and Access | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Smoke Test App (Few basic flows and validate app data) | bar: 2017-06-05 to 2017-06-12; 2017-07-17
Prepare | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Validate Functionality of Business Scenarios to script | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Validate Test Data (transactional and user access data) |  |  |  |  | 2017-07-24: >> Scripting new Sprint(8,9 & 10) usecases <<
Setup/Validate Test Tool Infrastructure (test load drivers) | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Test Script Creation (Web, iOS, UX) | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Validate scripts | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Conduct Test Readiness Review | bar: 2017-06-19 to 2017-07-03; 2017-07-24 to 2017-07-31
Execute | bar: 2017-07-03 to 2017-07-17; 2017-07-31 to 2017-08-21
Execute Baseline, 10% - 100% Peak Load Testing | bar: 2017-07-03 to 2017-07-17; 2017-07-31 to 2017-08-21
Report - Prepare & Present Final Report | bar: 2017-08-28
| Application Example ==>>> |  |  |  | 2017-06-05: ITPS Weather
Role | Resource Location |  |  | Rate | Prep Week1 | Prep Week2 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Total
Performance Lead | US |  |  | 140 |  |  | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 72800
Perf Tester #1 | IN |  |  | 24 |  |  | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 12480
Perf Tester #2 | IN |  |  | 22 |  |  | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 11440
Perf Tester #3 | IN |  |  | 22 |  |  | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 11440
|  |  |  | Total Cost ==> |  |  | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 8320 | 108160
Milestone Summary
|  |  |  | Start | 2017-05-22: End; 2017-05-29: Activity Description:
| Environment Pre-Reqs |  |  | 2017-05-22 | 2017-05-22: 2017-06-09; 2017-05-29: WFS System Admin Team & Development Team >> To Start and Complete the following: * Environment setup for Performance Testing * Sync Mobile App Build to Perf Environment * Setup/Loading of production like data volumes * Test Data for Performance Test Scripts must be established to facilitate Performance Test Scripting (and full set of Test Data to be ready by Test Execution start) * Configuration of any APP dependencies - like third party interfaces ,Stub etc. * Setup Env monitoring tools
|  |  |  | 2017-06-05 | 2017-05-22: 2017-06-16; 2017-05-29: WFS & IBM to Finalize performance use cases from sprint 1-7,validate functionality, validate test data provided by WFS,setup load tools etc
|  |  |  | 2017-06-19 | 2017-05-22: 2017-07-07; 2017-05-29: IBM team to script identified use cases and start baselining the same
|  |  |  | 2017-07-03 | 2017-05-22: 2017-07-21; 2017-05-29: IBM PT Team to start load testing the scripts developed in stages ( 25%,50% up to 100% load) and collect metrics
|  |  |  | 2017-07-17 | 2017-05-22: 2017-07-21; 2017-05-29: WFS and Dev team to deploy new sprints( Sprint 8 & 9) after QA validation. Sprint 10 to be deployed on July31 post QA valdation
|  |  |  | 2017-07-17 | 2017-05-22: 2017-07-21; 2017-05-29: WFS & IBM to Finalize performance usecases for sprint 8 & 9 incl 10*,validate functionality, provide testdata req to WFS. *Assume Sprint 10 would be ready by July 31st
|  |  |  | 2017-07-24 | 2017-05-22: 2017-08-04; 2017-05-29: IBM team to script identified usecases and start baselining the same
|  |  |  | 2017-08-07 | 2017-05-22: 2017-08-25; 2017-05-29: End To End load testing of all Sprints (1-10)
|  |  |  | 2017-08-28 | 2017-05-22: 2017-08-31; 2017-05-29: Submit Final Report
|  | KEY NOTES: | 1 | Any Delay in milestones will have cascading effect and result in slippage of dates or compromising on quality of deliverables
|  |  | 2 | Tests are limited to performance and load test of max duration 2hrs each. Endurance and Stress test (driving greater than 100% load) is not included in this effort
|  |  | 3 | Test data provided by WFS needs to be accurate, reliable and re-usable. Data should be provided upfront before the test
|  |  | 4 | Changes in APP that result in breaking of scripts, will require re-scripting
|  |  | 5 | ONLY iPad Mobile APP is estimated in this effort. (Falcon and OFP - Online Flight Plan - is assumed to be interfacing with App)
|  |  | 6 | ONLY QA passed Final builds to be provided to IBM Perf Team for scripting. Build should not have any Sev1 & Sev2 defects. Build blocking performance usecases would be rejected
|  |  | 7 | WFS BA's, Product SME's to provide technical inputs like App Navigations, Usecases for scripting,Testdata,Test window, Access and point of contacts for other guidance.
Note - IBM PT team would need 1-3+ hrs each day during planning phase from WFS team(SMEs and BA's)
|  |  | 8 | WFS to identify Approvers for Testplan,Testcases,Test design,test window ,results etc
|  |  | 9 | Results and Finding from each test would be shared with the team after consolidation of relavant logs,reports and data from tools.

## Actvity Plan
No | Activity | Start Date | End Date | % Comp | Status | Blockers | Comments
1 | Perf team on-boarded, Env Identified | 2017-08-13 | 2017-08-25 | 100%
2 | QA Test Env up and running - all access provided | 2017-08-13 | 2017-08-26 | 100%
| LR scripting in progress | 2017-08-28 | 2017-09-09 | 10%
| Batch Job requirement gathering and aceess in progress | 2017-08-28 | 2017-09-09 | 75%
8 | Development of LR Scripts + Complete Preparation of Batch Jobs | 2017-09-11 | 2017-09-15
9 | Dvelope 2 LR scripts (Query/BOL dash board + Tender Reprice) | 2017-09-11 | 2017-09-15
10 | Identify test data for batch jobs (2) | 2017-09-11 | 2017-09-15
11 | Gather batch jobs execution details (2) | 2017-09-11 | 2017-09-15
12 | Dry run 2 batch Jobs | 2017-09-15 | 2017-09-15
13 | Development of LR Scripts + Complete Preparation of Batch Jobs | 2017-09-18 | 2017-09-22
14 | Dvelope 2 additional LR scripts | 2017-09-18 | 2017-09-20
15 | Identify test data for batch jobs (2) | 2017-09-18 | 2017-09-19
16 | Gather batch execution details (2) | 2017-09-20 | 2017-09-22
17 | Dry run 2 batch Jobs | 2017-09-22 | 2017-09-22
18 | Development of LR Scripts + Complete Preparation of Batch Jobs | 2017-09-25 | 2017-09-29
19 | Dvelope 1 additional LR scripts | 2017-09-25 | 2017-09-26
20 | Prepare LR Scripts for dry run execution | 2017-09-26 | 2017-09-26
21 | Identify test data for batch jobs (5) | 2017-09-27 | 2017-09-27
22 | Gather batch execution details (5) | 2017-09-27 | 2017-09-27
23 | Dry run 5 batch Jobs | 2017-09-28 | 2017-09-29
24 | Modify LR Scripts + Complete Preparation of Batch Jobs | 2017-10-02 | 2017-10-06
25 | Modify LR Scripts | 2017-10-02 | 2017-10-02
26 | Execute a 25 users performance test | 2017-10-03 | 2017-10-03
27 | Execute Perforamnce Test of 10 Batch Jobs | 2017-10-03 | 2017-10-03
28 | Identify test data for batch jobs (5) | 2017-10-04 | 2017-10-06
29 | Gather batch execution details (5) | 2017-10-04 | 2017-10-04
23 | Dry run 5 batch Jobs | 2017-10-04 | 2017-10-04
30 | Modify LR Scripts + Complete Preparation of Batch Jobs | 2017-10-09 | 2017-10-13
31 | Modify LR Scripts | 2017-10-09 | 2017-10-09
32 | Execute a 50 users performance test | 2017-10-10 | 2017-10-10
33 | Execute Perforamnce Test of 15 Batch Jobs | 2017-10-11 | 2017-10-11
34 | Identify test data for batch jobs (5) | 2017-10-12 | 2017-10-13
35 | Gather batch execution details (5) | 2017-10-13 | 2017-10-13
23 | Dry run 5 batch Jobs | 2017-10-13 | 2017-10-13
36 | Modify LR Scripts + Complete Preparation of Batch Jobs | 2017-10-16 | 2017-10-20
37 | Modify LR Scripts | 2017-10-16 | 2017-10-16
38 | Execute a 75 users performance test | 2017-10-17 | 2017-10-17
39 | Execute Perforamnce Test of 20 Batch Jobs | 2017-10-18 | 2017-10-18
40 | Identify test data for batch jobs (5) | 2017-10-19 | 2017-10-20
41 | Gather batch execution details (5) | 2017-10-19 | 2017-10-20
42 | Modify LR Scripts + Complete Preparation of Batch Jobs | 2017-10-23 | 2017-10-27
43 | Modify LR Scripts | 2017-10-23 | 2017-10-23
44 | Execute a 100 users performance test | 2017-10-24 | 2017-10-24
45 | Execute Perforamnce Test of all Batch Jobs | 2017-10-25 | 2017-10-25
46 | Prepare Test Report | 2017-10-25 | 2017-10-27